## Guidelines
Tab | Purpose
Guidelines | This worksheet. The purpose of this worksheet is to provide general guidance on the content of each worksheet in this template.
Change Log | This worksheet provides basic information about the change.
Pre-Deployment Checklist | This worksheet provides a list of tasks, requirements, and validations that must be completed before starting the deployment activities
Runbook | This worksheet contains all the task details associated with thedeployment of our i-ARM solution. Note: Some steps in this Run Book may vary depending on updates from Microsoft or changes in the permissions granted to the team. Please consult the Infotechtion team if discrepancies arise.
Issue Log | All issues associated with the deployment or backout must be recorded in this worksheet. Any technical failure of a task and any remedial activity represents an issue.
Roll Back Steps | This section outlines the steps that should be taken in case the deployment fails. It includes details such as the conditions that warrant a rollback, the steps required to initiate a rollback, and the verification steps required to confirm that the rollback was successful.

## Change Log (hidden)
i-ARM Solution Deployment
Description
Date | Changes | Modified By
2024-11-18 | First Draft | Sunil K.G.
2024-11-25 | Updated section for PowerAutomate in the Run book Worksheet | Ritika Chauhan
2024-11-26 | Updated section for PRM section in the Run book Worksheet | Sunil K.G.

## Pre - Deployment Checklist
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Azure Subscription | Identify an Azure Subscription else a new subscription is to be provisioned | Customer
2 | Azure Subscription | Ensure that all Resource Providers are registered as per the i-ARM Detailed Design Document | Customer
3 | Azure Resource Group | Azure Resource Group is created in the subscription identified in the first step | Customer
4 | Power Automate | Confirm that Power Automate premium licenses are available, minimum 2 Licenses are required | Customer
5 | Power BI | Confirm the availability of Power BI Pro or Premium licenses and create a Power Bi workspace. | Customer
7 | Process | Identify and share the processes required for creating or modifying services in the Azure environment, such as: o Service tickets for creating Service Principals o Requests for assigning permissions to resources (e.g., applying RBAC roles) o Any approval workflows or documentation needed for service configuration changes in the environment. | Customer
8 | Certificates | Nine certificates are required for the i-ARM solutions, each with a 3-year expiry (both .cer and .pfx formats needed). The certificates must be issued by a Certified Authority (CA). | Customer
9 | Design Document | Confirm that the i-ARM Detailed Design Document has been reviewed | Customer
10 | Azure Resources | Validate the following against the shared i-ARM Detailed Design Document o Any Client Specific Naming Convention for azure resources o Database & Virtual Machine Login Id Password o Virtual Network IP Range o Azure Resources SKUs (Pricing Tier) | Customer
11 | Permission | Identify a user or group with Owner permissions on the subscription, this is required to add permissions for resources (applying RBAC roles). | Customer
12 | Permission | The API permission requires Write or Full Control access on specific service principals needed for i-ARM operations. Please review the API permissions outlined in the i-ARM Detailed Design Document. | Customer
13 | Service Principals Creations | Ensure that Service Principals are created in accordance with the specifications outlined in the i-ARM Detailed Design Document. | Customer
|  | Verify that Service Principals have been granted the required API permissions with Global Admin consent, as specified in the i-ARM Detailed Design Document. | Customer
|  | Ensure that Service Principals have secrets created as outlined in the i-ARM Detailed Design Document, and ensure the secrets are captured this is required for key vault configurations. | Customer
14 | Service Account | Create service accounts with the necessary permissions and licenses as defined in the i-ARM Detailed Design Document. | Customer
15 | Entra Id Groups | Create Entra ID groups based on the specifications outlined in the i-ARM Detailed Design Document. Ensure the Service accounts have necessary permissions and roles assigned. | Customer
16 | Entra Id Groups | Identify the users and add them to the appropriate Entra ID groups. | Customer
17 | Permission | Grant "Contributor" permission to the Azure resource group (refer step 3) for the DevOps Service Principal (spn-devopsconn-iarm-deploy-prd). | Customer
18 | Permission | Add Infotechtion Deployment team members into the Entra ID group (sg-sub-iarm-reader-prd) | Customer
19 | Permission | Assign "Reader" access to the subscription (as mentioned in step 3) for the Entra ID group (sg-sub-iarm-reader-prd) Note: The Owner role at the Resource Group level allows the Infotechtion Team to perform majority of their tasks (Assign Roles and Configurations on resources). | Customer
20 | Service Principals | Share the following details with Infotechtion Team to create the DevOps Service Connection Tenant ID Azure Subscription ID Azure Subscription Name DevOps SPN (spn-devopsconn-iarm-deploy-prd) Client ID DevOps SPN (spn-devopsconn-iarm-deploy-prd) Client Secret | Customer
21 | SharePoint (PRM) | Validate the SharePoint Apps Catalog, SharePoint ContentType Hub, SharePoint Search has been created and enabled. | Customer
22 | SharePoint (PRM) | Create a new SharePoint site collection for Physical Records Management | Customer
23 | SharePoint (PRM) | Add the Entra ID group (sg-sub-iarm-reader-prd) as a Site collection administrator for the site identified for physical records management Add the Entra ID group (sg-sub-iarm-reader-prd) as a Owner to the Content Type hub site collection (https://{TenantName}.sharepoint.com/sites/contenttypehub) | Customer
24 | SharePoint (PRM) | Identify an SME who has SharePoint Administrator permissions, This is required for configuring the term store, content type hub, SPFx deployment and search configurations. | Customer
25 | Power Automate | The PowerAutomate solution will be deployed exclusively to the default environment. | Customer
26 | Power Automate | Ensure the power automate premium connectors are allowed "Microsoft 365 Compliance, Azure Key Vault, Microsoft Dataverse, SQL Server, HTTP " | Customer
27 | Compliance Actions | The Retention Label and Retention Label policies have been defined | Customer
28 | Permission | Identify a user for creating and managing Retention lables and Retention label policy. Add the user to Records Management Role Group in Microsoft Purview Compliance Portal. Note: The retention labels supporting i-ARM disposition workflows can only be created after Power Automate solutions are imported into the Customers Default Power Automate environment. Note: It is recommended that the service account designated for Power Automate be used for creating retention labels and that this service account be added to the "Compliance Administrator" role group in the Microsoft Purview Compliance Portal. | Customer
29 | Firewall | Ensure the Devops firewall rule shared in the i-ARM detailed Design Document is added for establishing connectivity to Infotechtion Azure DevOps | Customer
30 | Script Execution | Identify a machine (Company workstation or Virtual Machine) for executing scripts required for Syncing Labels and for Physical Records deployment. | Customer
31 | IaC | Identify the appropriate Infrastructure as Code (IaC) template for the deployment and share any specific standards that need to be considered. IaC deployment will be carried out by the Infotechtion team. | Customer
32 | SharePoint (PRM) | For configuring Physical Records Management, ensure PowerShell version 7.4.3 or higher is installed, along with the PnP PowerShell module version 2.4.0, on the workstation listed in the pre-deployment checklist (Script Execution). | Customer
33 | MPIP | MPIP Scanner requries one Sensitivity label published to the scanner account (Service account identified for MPIP scanner) | Not Applicable
34 | NFS | VM user Id and password required for NFS set up (will be covered during the iARM infra set up) | Not Applicable
35 | NFS | For scanning the Network file share the network files shared should be mounted on the VM identified for NFS and the Network file shares should be accessible for user in the VM | Not Applicable

## Run Book
Plan Start Date
i-ARM Runbook
Installation Pre-requisites: This section ensures that all dependencies like network configurations, permissions, and any other foundational setups are in place, allowing the installation to proceed smoothly and avoid errors. |  |  |  |  | 38
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Service Principals Configuration | Ensure Service Principals are created based on iARM Design Document shared. Below are the list | Customer |  | 6
2 | Service Principals | spn-wapp-iarm-uidirectoryaccess-prd | Customer
3 | Service Principals | spn-func-iarm-apiauth-prd | Customer
4 | Service Principals | spn-func-iarm-urclabelsync-prd | Customer
5 | Service Principals | spn-func-iarm-graphapi-prd | Customer
6 | Service Principals | spn-devopsconn-iarm-deploy-prd | Customer
7 | Service Principals | spn-func-iarm-notifications-prd | Customer
8 | Service Principals | spn-mydisppa-iarm-spoaccess-prd | Customer
9 | Service Principals | spn-func-iarm-mydispconnspoaccess-prd | Customer
10 | Service Principals | spn-sql-iarm-sqlaccess-prd | Customer
11 | Service Principals | spn-func-iarm-prmprovisioning-prd | Customer
12 | Service Principals | spn-func-iarm-prmbulkimport-prd | Customer
13 | Service Principals | spn-func-iarm-prmsync-prd | Customer
14 | Service Principals | spn-wj-iarm-m365auditsync-prd | Customer
15 | Service Principals | spn-agent-iarm-downloadarchiveblobs-prd | Customer
16 | Service Principals Configuration | Verify that Service Principals have the required API permissions added as per the iARM Design Document and the Global Admin Consent is granted by them by a Global Administrator | Customer |  | 6
17 | Service Principals Configuration | Ensure that Service Principals have secrets created as specified in the iARM Design Document. Ensure the Secrets are stored as it is required in configuration steps below | Customer |  | 2
18 | Service Principals | Verify that the DevOps Service Principal (spn-devopsconn-iarm-deploy-prd) has a secret created and share the following details with Infotechtion Team to create the DevOps Service Connection where I-ARM would be deployed Tenant ID Azure Subscription ID Azure Subscription Name DevOps SPN Client ID DevOps SPN Client Secret | Customer |  | 0.5
19 | Permission | Add the DevOps Service principals (spn-devopsconn-iarm-deploy-prd) as Contributor to the resource group where i-ARM would be deployed | Customer |  | 0.5
20 | Service Account | Create service accounts with the necessary permissions and licenses based on iARM Design Document | Customer |  | 4
21 | Entra Id Groups | Create Entra ID groups based on iARM Detailed Design Document and Ensure the below Entra ID groups have been created | Customer |  | 6
22 | Entra Id Groups | sg-sub-iarm-reader-prd | Customer
23 | Entra Id Groups | Add Infotechtion team members to "sg-sub-iarm-reader-prd" group | Customer
24 | Entra Id Groups | sg-svc-iarm-webappadministrators-prd | Customer
25 | Entra Id Groups | sg-svc-iarm-sqlentraadministrators-prd | Customer
26 | Entra Id Groups | Identify and add users to all the Entra ID groups | Customer
27 | Permission | Assign Reader access to the Azure Subscription for the Entra ID group (sg-sub-iarm-reader-prd). Note: The Owner role at the Resource Group level allows the Infotechtion Team to perform majority of their tasks (Assign RBAC Roles and Configurations on resources). | Customer |  | 0.5
28 | Permission | Verify that the Infotechtion users in the Entra ID group (sg-sub-iarm-reader-prd) can access the resource group created for the i-ARM deployment | Infotechtion
29 | Physical Records Management | For configuring Physical Records Management, ensure PowerShell version 7.4.3 or higher is installed, along with the PnP PowerShell module version 2.4.0, on the workstation listed in the pre-deployment checklist. | Customer |  | 0.5
30 | Power BI | Ensure the service account identified for publishing Power Bi reports has Power BI Workspace Owner permission added. Refer the i-ARM Detailed Design Document for the Service Account details | Customer |  | 0.5
31 | Power Automate | Ensure the service account identified for Power Automate has "Environment Maker role" permission granted. This is required for importing the solution. Refer the i-ARM Detailed Design Document for the Service Account details | Customer
32 | Power Automate | Ensure the service account identified for Data Gateway has "Environment Maker role" permission granted. This is required for importing the solution. Refer the i-ARM Detailed Design Document for the Service Account details | Customer
33 | Power Automate | Create two work queues in the default environment where the i-ARM Disposal Power Automate flows will be imported. For detailed instructions, please refer to the Deployment Guide. | Customer |  | 0.5
34 | Power Automate | Check the Power Automate Admin Center to ensure that there are no DLP policies in place that block the using of connectors. | Customer |  | 0.5
35 | IaC | Identify the appropriate Infrastructure as Code (IaC) template for the deployment and share any specific standards that need to be considered. IaC deployment will be carried out by the Infotechtion team. | Customer |  | 0.5
36 | Certificates | Eight self-signed certificates are required for the i-ARM solutions, each with a 3-year expiry (both .cer and .pfx formats needed). The certificates must be issued by a Certified Authority (CA). Store the Certificates in a safe location (Customer Workstation) | Customer |  | 0.5
37 | SharePoint (PRM) | Make a note of the SharePoint Site created for Physical records management and verify that the Entra ID group (sg-sub-iarm-reader-prd) is added as a Site collection administrator for the site. | Customer
38 | Power Automate | Identify or mutually agree a shared location where the solution can be shared | Customer with Infotechtion Support |  | 0.5
39 | Power Bi | Identify or mutually agree a shared location where the Power Bi reports can be shared | Customer with Infotechtion Support
40 | SharePoint (PRM) | Identify or mutually agree a shared location where the Scripts and SharePoint Framework package required for Physical Records management can be shared | Customer with Infotechtion Support
41 | SharePoint (PRM) | Ensure the Terms are identified required for Physical Records Management 1. HomeLocation 2. Office Address 3. Media 4. Country of Jurisdiction 5. Business 6. Business Function 7. Business Process 8. Business Unit / region 9. Legal Entity 10. Language 11. Security Classification | Customer with Infotechtion Support |  | 1
42 | Validation | Validate that all the pre-requiestes are set up based on the iARM Design Document shared | Infotechtion |  | 8
i-ARM Infrastructure Creation: This section is required for setting up the infrastructure required for the i-ARM application |  |  |  |  | 36.5
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | IaC template | Modify the IaC template based on any changes identified during Pre - Deployment Checklist validation / Customer Engagement Note: This is based on the assumption that Bicep templates will be used. | Infotechtion |  | 16
2 | Azure Devops | Set up the Azure DevOps service connection in the Infotechtion DevOps environment using an Service Principal credentials. Validate the service connection to ensure it is functioning correctly and has the necessary permissions. | Infotechtion |  | 0.5
3 | Azure Devops | Execute IaC Deployment through Azure Devops | Infotechtion |  | 5
4 | Azure Resources | Validate that the below resources are created based on i-ARM Detailed Design Document shared Note: Supporting resources will be created for some of the Azure resources listed below. | Infotechtion |  | 1
5 | Application Insights | 9 Application insights | Infotechtion
6 | App Service plan | 9 Service plans | Infotechtion
7 | App Service | 2 App Service | Infotechtion
8 | Bastion | 1 Bastion | Infotechtion
10 | Container registry | 1 Container Registry | Infotechtion
11 | Function App | 7 Function Apps | Infotechtion
12 | Function App | Ensure all the Function Apps are created with .Net version 8 isolated | Infotechtion
13 | Key vault | 1 Key Vault | Infotechtion
14 | Log Analytics workspace | 1 Log Analytics | Infotechtion
15 | Network security group | 6 Network Security Group | Infotechtion
16 | Private DNS zone | 6 Private DNS zone | Infotechtion
17 | Storage account | 9 Storage Accounts | Infotechtion
18 | SQL database | 1 SQL Database | Infotechtion
19 | SQL server | 1 SQL Server | Infotechtion
20 | Virtual machine | 1 Virtual Machine | Infotechtion
21 | Network Interface | 1 Network Interface | Infotechtion
22 | Managed identity | 1 Managed identity | Infotechtion
23 | Virtual network | 1 Virtual Network | Infotechtion
17 | Virtual Machine | Validate the Virtual Machine can be logged in using the credentials created | Customer with Infotechtion Support
24 | Azure | Log in to Azure Portal with an account (Contribute permission to resource group, identified during pre-deployment activities) that has the required permissions to assign RBAC roles and perform configuration tasks on Azure resources in the specified Azure subscription/resource group where i-ARM is deployed. Note: If the sg-sub-iarm-reader-prd group has been granted Owner permissions, the Infotechtion team will be able to perform the following activities | Customer |  | 1
25 | Log Analytics workspace | Share Primary Key for Log Analytics to Infotechtion Team | Customer
26 | Permission | Provide ACR pull permission for managed Identity to the Container registry | Customer
27 | Permission | Provide permission to Infotechtion DevOps Agent for the Pull operation (Internal operation) | Infotechtion |  | 2
28 | IaC template | Modify the IaC template for creating Container Instance | Infotechtion
29 | Azure Devops | Execute IaC Deployment through Azure Devops | Infotechtion |  | 2
30 | Azure Resources | Validate that the below resource is created and the agent is running | Infotechtion
31 | Container instances | 1 Container Instance | Infotechtion
32 | Permission | Provide the "StorageBlobDatareader" RBAC role to the Service Principal "spn-agent-iarm-downloadarchiveblobs-prd" for Storage account "saiarmarchiveuksouthprd" using the account identified (First Task under i-ARM Infrastructure Configuration) | Customer with Infotechtion Support |  | 1
33 | Permission | Provide the "StorageBlobDatareader" RBAC role to the Service Account (Refer the Detailed design document) for Storage account "saiarmarchiveuksouthprd" using the account identified (First Task under i-ARM Infrastructure Configuration) | Customer with Infotechtion Support
34 | Permission | Ensure the Service principal has been assigned the Key Vault Secret User and Key Vault Certificate User roles for the key vault created in the resource group. | Customer with Infotechtion Support
35 | Power Automate | Provide the "StorageBlobDatacontributor" RBAC role to the Service Account identified for Power Automate (Refer the Detailed design document) for Storage account "saiarmarchiveuksouthprd" using the account identified (First Task under i-ARM Infrastructure Configuration) | Customer with Infotechtion Support
36 | Power Automate | Ensure the service account identified for Power Automate has been assigned the Key Vault Certificates Officer and Key Vault Secrets Officer roles for the key vault created in the resource group. | Customer with Infotechtion Support
37 | Azure Firewall | Verify Azure Firewall configurations are configured with the specifications as shared i-ARM Detailed Design Document. | Customer |  | 4
38 | Physical Records Management | Identify and locate where the scripts and package (SPFx) have been shared. | Customer with Infotechtion Support |  | 4
39 | Physical Records Management | Identify the workstation for script execution and upload the scripts and package to it. | Customer with Infotechtion Support
40 | Physical Records Management | Identify the SME who has SharePoint Administrator permissions and the script should be executed by the said SME | Customer with Infotechtion Support
41 | Physical Records Management | Import the Terms into the TermStore | Customer with Infotechtion Support
42 | Physical Records Management | Verify that the Service Principal (spn-func-iarm-prmprovisioning-prd) has an uploaded certificate, and ensure the following details are available on the workstation for script execution: Tenant ID spn-func-iarm-prmprovisioning-prd SPN Client ID spn-func-iarm-prmprovisioning-prd SPN Certificate Thumbprint SharePoint Site Identified for PRM AdminSiteUrl ContentTypeHubUrl | Customer with Infotechtion Support
43 | Physical Records Management | Execute the Scripts in the order below 1. MasterProvisioning.ps1 2. PublishPackage.ps1 (This should be executed by the SME who has SharePoint Administrator permission) 3. Site.Selected.ps1 (This is for adding permission for Bulk Operations) | Customer with Infotechtion Support
i-ARM Infrastructure Configuration: This section entails setting up and fine-tuning the infrastructure parameters specific to i-ARM. Please refer the Deployment Guide for detailed instructions |  |  |  |  | 17
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Azure | Log in to Azure Portal with an account (Contribute permission to resource group, identified during pre-deployment activities) that has the required permissions to assign RBAC roles and perform configuration tasks on Azure resources in the specified Azure subscription/resource group where i-ARM is deployed. Note: If the sg-sub-iarm-reader-prd group has been granted Owner permissions, the Infotechtion team will be able to perform the following activities | Customer |  | 0.5
2 | Azure resources | Capture the endpoints for Function Apps and WebApp | Customer with Infotechtion Support
3 | Service Principal | Update Service Principal with expose an API & Redirects with endpoints captured in previous task | Customer with Infotechtion Support
4 | Key Vault | Provide the below RBAC role for Key vault for the account identified (First Task) | Customer with Infotechtion Support |  | 0.5
5 | Key Vault | Key Vault Certificates Officer | Customer with Infotechtion Support
6 | Key Vault | Key Vault Secrets Officer | Customer with Infotechtion Support
7 | Key Vault | Use Virtual Machine for adding Secrets and Creating Certificates in KeyVault | Customer with Infotechtion Support
8 | Key Vault | Create Key Vault Secrets | Infotechtion |  | 1
9 | Key Vault | Upload Certificates into Key Vault | Infotechtion |  | 1
11 | Service Principal | Upload Certificates (.cer) to Service Principals | Customer |  | 1
12 | Function App My Data Module | Validate System Assigned Identity for Function App | Infotechtion |  | 6
13 | Function App My Data Module | Assign roles to managed identity | Infotechtion
14 | Function App My Data Module | Configure Function Apps Authentication | Infotechtion
15 | Function App My Data Module | Add/Update Environment Variables in Function App | Infotechtion
16 | Function App My Data Module | Ensure the CORS has been updated | Infotechtion
17 | Function App My Disposal Dashboard Module | Validate System Assigned Identity for Function App | Infotechtion
18 | Function App My Disposal Dashboard Module | Assign roles to managed identity | Infotechtion
19 | Function App My Disposal Dashboard Module | Configure Function Apps Authentication | Infotechtion
20 | Function App My Disposal Dashboard Module | Add/Update Environment Variables in Function App | Infotechtion
21 | Function App My Disposal Dashboard Module | Ensure the CORS has been updated | Infotechtion
22 | Function URC Module | Validate System Assigned Identity for Function App | Infotechtion
23 | Function URC Module | Assign roles to managed identity | Infotechtion
24 | Function URC Module | Configure Function Apps Authentication | Infotechtion
25 | Function URC Module | Add/Update Environment Variables in Function | Infotechtion
26 | Function PRM Bulk Import | Validate System Assigned Identity for Function App | Infotechtion
27 | Function PRM Bulk Import | Assign roles to managed identity | Infotechtion
28 | Function PRM Bulk Import | Configure Function Apps Authentication | Infotechtion
29 | Function PRM Bulk Import | Add/Update Environment Variables in Function | Infotechtion
30 | Function PRM Sync Module | Validate System Assigned Identity for Function App | Infotechtion
31 | Function PRM Sync Module | Assign roles to managed identity | Infotechtion
32 | Function PRM Sync Module | Configure Function Apps Authentication | Infotechtion
33 | Function PRM Sync Module | Add/Update Environment Variables in Function | Infotechtion
34 | Function App m365auditconnector Module | Validate System Assigned Identity for Function App | Infotechtion
35 | Function App m365auditconnector Module | Assign roles to managed identity | Infotechtion
36 | Function App m365auditconnector Module | Configure Function Apps Authentication | Infotechtion
37 | Function App m365auditconnector Module | Add/Update Environment Variables in Function | Infotechtion
38 | Function App m365dispconnector | Validate System Assigned Identity for Function App | Infotechtion
39 | Function App m365dispconnector | Assign roles to managed identity | Infotechtion
40 | Function App m365dispconnector | Configure Function Apps Authentication | Infotechtion
41 | Web Job | Validate System Assigned Identity for WebJob | Infotechtion
42 | Web Job | Assign roles to managed identity | Infotechtion
43 | Web Job | Add/Update Environment Variables in WebJob | Infotechtion
44 | Data Base | Set the Entra ID group (iarm-portal-sql-entraid-administrators-prd) as Admin on the SQL Server | Infotechtion |  | 4
45 | Data Base | Configure the SQL Server to support both Microsoft Entra authentication and SQL authentication | Infotechtion
46 | Data Base | Execute Database Access Scripts for Service Principal and Managed Identity Access | Infotechtion
47 | Data Base | Execute Database schema scripts | Infotechtion
48 | Data Base | Execute delta scripts for index creation | Infotechtion
49 | Physical Records Management | Validate the Physical Records Management SharePoint Site has 1. Bulk Import Logs List Created 2. Bulk Import Queue List Created 3. Archive Box List List Created 4. Physical Record List List Created 5. App is deployed 6. SharePoint Site Pages Created (Physical Records, Archive box, Search pages...) 7. SharePoint groups Created | Infotechtion |  | 3
50 | Physical Records Management | Configure Search for Physical Records Management | Infotechtion
51 | Physical Records Management | Configure Refinable Strings Note: We may require few data for Configuring Search | Infotechtion
52 | Physical Records Management | Create and configure the SharePoint pages for Physical Records Management, Archive Box and Search | Infotechtion
i-ARM Agent Configurations: This section outlines the steps for deploying the i-ARM agents - Per Node |  |  |  |  | 10
1 | NFS Configuration | NFS configurations with iARM database, Install Certificate on VM | Infotechtion |  | 4
2 | NFS Configuration | Upload Certificate to SPN and capture information required for the installation of NFS | Customer
3 | NFS Agent Deployment | Start MSI Installer and ensure the service is running from current logged in user | Infotechtion
4 | MPIP (Microsoft Purview Information Protection scanner) | MPIP Scanner Set Up | Infotechtion |  | 6
5 | MPIP | MPIP database Set UP | Infotechtion
6 | MPIP | MPIP Scanner Configurations | Infotechtion
7 | MPIP | MPIP Scanner Configurations (Purview) | Customer
i-ARM Solution Deployment: This section outlines the steps for deploying the i-ARM solution and the validation process after the solution has been deployed. |  |  |  |  | 7.5
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Azure Devops | Update the necessary values in the Azure Variable Group configuration for the UI environment Deployment. | Infotechtion |  | 0.5
2 | Azure Devops | Deploy the i-ARM solutions using Infotechtion Azure DevOps pipelines | Infotechtion |  | 4
3 | Azure | Ensure that the functions within the "func-iarm-urc-uksouth-prd" Function App are visible. | Infotechtion |  | 2
4 | Azure | Ensure that the functions within the "func-iarm-mydisp-uksouth-prd" Function App are visible. | Infotechtion
5 | Azure | Ensure that the functions within the "func-iarm-mydata-uksouth-prd" Function App are visible. | Infotechtion
6 | Azure | Ensure that the functions within the "func-iarm-prmbulk-uksouth-prd" Function App are visible. | Infotechtion
7 | Azure | Ensure that the functions within the "func-iarm-prmsync-uksouth-prd" Function App are visible. | Infotechtion
8 | Azure | Ensure that the functions within the "func-iarm-m365auditconnector-uksouth-prd" Function App are visible. | Infotechtion
9 | Azure | Ensure that the functions within the "func-iarm-m365dispconnector-uksouth-prd" Function App are visible. | Infotechtion
10 | Azure | Ensure the Azure Web App has been deployed | Infotechtion
11 | Azure | Ensure the Azure Web Job has been deployed | Infotechtion
12 | Data Base | Review database to ensure all latest changes are covered | Infotechtion
13 | Power Automate | Import the Power Automate Solution into the Default Environment | Customer with Infotechtion Support |  | 1
14 | Power Automate | Add steps for Connection Reference - During the import process, you will be prompted to provide the connection details. | Customer with Infotechtion Support
15 | Power Automate | Update the Environment variables to customer specific values | Customer with Infotechtion Support
16 | Power Automate | Validate there are 7 Flows visible in the solution and all are Turned on | Customer with Infotechtion Support
i-ARM Solution Post Deployment Configuration : This section refers to the tasks and settings applied after the i-ARM solution has been deployed, ensuring that the environment is optimized, properly configured, and aligned with operational and security requirements for ongoing management and performance. |  |  |  |  | 15.5
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Azure | Log in to Azure Portal with an account (Contribute permission to resource group, identified during pre-deployment activities) that has the required permissions to assign RBAC roles and perform configuration tasks on Azure resources in the specified Azure subscription/resource group where i-ARM is deployed. Note: If the sg-sub-iarm-reader-prd group has been granted Owner permissions, the Infotechtion team will be able to perform the following activities | Customer |  | 1
2 | Route Table | Create route tables in the customer environment | Customer
3 | Route Table | Configure rules for the route tables | Customer |  | 2
4 | Azure Firewall | Verify Azure Firewall configurations are configured with the specifications as shared i-ARM Detailed Design Document. | Customer |  | 4
5 | Virtual Machine | Validate that the internet is enabled. | Customer |  | 0.5
6 | Data Gateway | Install and Configure Datagateway on the Virtual Machine using the Service Account identified for Data gateway | Infotechtion |  | 2
7 | Power Bi | Install Power Bi Desktop on the Virtual Machine | Infotechtion
8 | Power Automate | Share the Power Automate flows with the user designated for creating labels in the Purview Compliance Center | Infotechtion |  | 1
9 | Power Automate | Create labels in Purview and associate them with the Power Automate flows. Note: The effort required may increase based on the number of labels identified. | Customer with Infotechtion Support
10 | Power Automate | Share the Gateway with the Service Account identified for Power Automate (Importing the flow). The steps should be performed on Power Automate Admin Center | Customer with Infotechtion Support |  | 1
11 | Power BI | Share the Gateway with the Service account identified for Power Bi. Create a new connection using the Gateway. Actions to be performed in Power Bi Service. | Customer with Infotechtion Support
12 | Power BI | Validate the Identified Service Account for Power BI has access to Power BI Workspace | Customer with Infotechtion Support |  | 0.5
13 | Power BI | Download the Power BI Templates into the Virtual Machine | Customer with Infotechtion Support |  | 0.5
14 | Power BI | Configuration of Power BI report using the Power BI template and Publish the reports | Infotechtion |  | 3
Review and testing : This refers to the process of evaluating the i-ARM solution post-deployment to ensure that all configurations, features, and functionalities are working as expected. This step involves validating system performance, identifying any issues, and performing tests to confirm that the deployment meets both technical and business requirements. |  |  |  |  | 18
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Unit Testing | Ensure the i-ARM portal loads successfully | Infotechtion |  | 16
2 | Unit Testing | Identify an Active Directory (AD) user for testing purposes | Infotechtion
3 | Unit Testing | Confirm that an AD user can log in to the i-ARM portal using valid credentials | Infotechtion
4 | Unit Testing | Verify that the "My Disposal Dashboard" is displayed in the navigation bar | Infotechtion
5 | Unit Testing | Validate that the "My Disposal Dashboard" loads correctly when selected from the navigation bar | Infotechtion
6 | Unit Testing | Verify business reviewer, archive reviewer, historic tabs are present in "My Disposal Dashboard" | Infotechtion
7 | Unit Testing | Verify filters icon is present in all 3 tabs of "My Disposal Dashboard" | Infotechtion
8 | Unit Testing | Verify 'manage' columns icon is present in all 3 tabs of "My Disposal Dashboard" | Infotechtion
9 | Unit Testing | Verify 'refresh icon' is present in all 3 tabs of "My Disposal Dashboard" | Infotechtion
10 | Unit Testing | Verify an alert message shows up in all 3 tabs of "My Disposal Dashboard" when no records are present stating possible reasons for no records | Infotechtion
11 | Unit Testing | Validate Forms are visible for both Physical Records and Archive box | Infotechtion
12 | Unit Testing | Verify the Physical Records Management search is working | Infotechtion
13 | Unit Testing | Recheck/Re-authenticate connection reference for each connector by clicking on ellipsis of each action. | Customer with Infotechtion Support
14 | Physical Records Management | Validate the SharePoint Site Identified for Physical Records Management can 1. Create a Physical Record 2. Create a Archive Box 3. Search pages are Visible. 4. Check search results are returning correct values. 5. Taxonomy Terms are in place | Customer with Infotechtion Support
15 | Unit Testing | Sanity for iarm Scanner | Infotechtion |  | 2
* Note: 1. Some steps in this Run Book may differ depending on updates from Microsoft or changes in the permissions granted to the team. Please reach out to the Infotechtion team if you notice any discrepancies. 2. Task Responsible (Infotechtion): It is assumed that the Infotechtion team has Owner permissions for the Resource Group, allowing them to deploy and configure Azure resources. 3. Any delays in obtaining approvals could affect the deployment schedule and overall effort. 4. This worksheet outlines all the tasks involved in deploying our i-ARM solution, assuming the Customer has reviewed and obtained the necessary approvals for onboarding iARM. 5. The effort estimate above applies to the deployment and configuration of iARM in each environment.

## Issue Log
Issue Log
ID | Date Raised | Raised By | Issue Owner | Issue Severity | Issue Description | Actions Taken | Action By | Issue Status | Date Closed | Closed By
1
2
3
4
5
6
7
8
9
10
11
12
13
14
15
16
17
18
19
20