## Examples (hidden)
The following step-by-step activities are included to show the level of detail will be included in Infotechtion runbook for each activity considered in the scope of TOM
Investigate incidents related to files with retention label deleted prematurely by a user action with administrative / elevated privileges.
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Generate the i-ARM weekly audit report. | Review the i-ARM audit report and look for total items synched and if any errors in weekly sync of audit logs between i-ARM and Microsoft Purview. | Cutomer technology team |  | 4
2 | Review Purview audit logs for labelling related audit | Generate the Purview audit log report for items with retention labelled, changed, removed or expired for Start - End Date of the audit report. | Cutomer technology team
3 | Reconcilliation of audit data | Compare key statistics from Purview audit log with i-ARM sync: - total items synced - Total errors in sync | Cutomer technology team
4 | Report errors i-ARM support | Raise a ticket with i-ARM support to investigate the sync errors. | Cutomer technology team
L2 Support - Management of critical / high severity alerts trigerred via Azure Monitor , including raising ticket with i-ARM product support.
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Log in to Azure Monitor associated with i-ARM resource group | Run the Azure log analytics query to identify Critical, High severity application errors. | Cutomer technology team |  | 6
2 | Review critical errors | Filter on critical errors and refer to i-ARM operational manual to identify the required actions. | Cutomer technology team
3 | Resolve Errors | Resolve errors as per the operational manual or collect additional information for raising a ticket with i-ARM support. | Cutomer technology team
4 | Raise Ticket | Raise a ticket with i-ARM support to investigate the sync errors. Based on the reponse raise a CRQ where a hot fix is required to address the issue. | Cutomer technology team
5 | Hot fix release | Release the hot fix for resolution in Non-Prod and Production environment. Perform sanity checks including repeat Step 1 to confirm the critical error is resolved. | i-ARM Support |  | 4
i-ARM feature release review and deployment of updates to non-production and production environment with supporting release notes and manuals
Sl.No | Task Category | Task Activity | Task Responsible | Task Assigned To | Effort (In Hour) | Task Status | Start Date | Completion Date | Validated By | Comments
1 | Release Notes | Present i-ARM release notes to Modern work, Security and RIA stakeholders. | i-ARM Support |  | 15
2 | Architecture Updates | Provide content for updating HLD and LLD copies of customer for internal review and sign off regards to new feature updates. | i-ARM Support
3 | Architecture Updates | Represent i-ARM in customer internal review forums to approve the updated design. | i-ARM Support
4 | Technical Change Request - NonProd / Prod | Coordinate and provide content for the change request process | i-ARM Support
5 | Technical Change implementation | Coordinate the configuration of release pipeline, perform the pre-deployment tasks and accordinate the access requests included as part of the change aproval. | i-ARM Support |  | 8
6 | Technical Change implementation | Follow the Infotechtion provided runbook shared with each release note to complete the deployment, configuration and post deployment checks including the security checks related to be binaries released into i-ARM resource group. Record and report success or failure (leading to regression of the release). | i-ARM Support |  | 20
7 | Technical Change implementation | Coordinate the user validation and communication to key stakeholders of the change outcome. Update service desk of the change and any relevant updates to support user enquiries and incidents related to the change. | i-ARM Support |  | 20
8 | Technical Change implementation | Finalise the change and confirm closure of the change request | i-ARM Support |  | 10

## Operational Activities
S.No. | Product Feature | Activity | frequency | Type | Responsibility | Estimated hrs for active work / event | Included in i-arm license | Offerred as addon service | Skills Required
1 | i-ARM Records lifecycle | Investigate incidents related to files with retention label deleted prematurely by a user action with administrative / elevated privileges. Note: User removed label - user deleted file. | Monthly | reactive | Customer | 4 | No | yes | Microsoft Purview Audit / Content Search, Powershell, KQL
2 | i-ARM Records lifecycle | Adhoc reports generation requested by records management team based on audit activities captured for digital and physical records. | on-demand | reactive | Customer | 20 | No | yes | Microsoft Purview Audit / Content Search, Powershell, KQL
3 | i-ARM Records lifecycle | Review of records overdue disposal review by business reviewer and trigger remediation review with records management / business team. | Monthly | proactive | Customer | 5 | No | yes | Powershell, Power BI
4 | i-ARM Records lifecycle | Coordinate Review / Transfer of records end of retention review ownership to address user responsibility changes aligned with the organisation change or leaver scenario. | Monthly | proactive | Customer | 40 | No | yes | Powershell
5 | i-ARM Records lifecycle | One-off change to update select label configuration to automatically dispose at the end of retention. Note: An interim configuration has been applied to prevent immediate disposition of migrated records. | on-demand | reactive | Infotechtion | 40 | yes | NA | Powershell
6 | i-ARM Records lifecycle | L2 Support - Management of critical / high severity alerts trigerred via Azure Monitor , including raising ticket with i-ARM product support. | on-demand | reactive | Customer | 6 | No | yes | Azure fundamentals, Azure Monitor query management.
7 | i-ARM Records lifecycle | Service desk queue management for user requests / issues related to i-ARM / records management, and transfer to L2 / L3 support. | on-demand | reactive | Customer | 3 | No | yes | Functional knowledge of Customer specific Service desk tool
8 | i-ARM Records lifecycle | i-ARM feature release review and deployment of updates to non-production and production environment with supporting release notes and manuals | Quarterly | proactive | Infotechtion | 73 | yes | NA | Azure architecture, Powershel, Azure devops, Key vault management, Azure firewall
9 | i-ARM Records lifecycle | Updates to i-ARM standard technical documentation, deployment procedures, runbooks and User manuals. | Quarterly | proactive | Infotechtion | 50 | yes | NA | Technical writing in Github
10 | i-ARM Records lifecycle | Support to Records Managers with issues related to i-ARM features with clarifications, workarounds and hotfixes. | on-demand | reactive | Infotechtion | 10 | yes | NA | Microsoft Purview, Powershell
11 | i-ARM Azure infrastructure | Health checks, system usage against infrastruture thresholds, updating certificates, Azure services consumption review and analysis for optimization for managing costs. Including review of i-ARM configurations at: - Azure Management Group and Subscription Organization - Azure landing zone - i-ARM subscription Configuration - i-ARM resource Group configuration - Connectivity Subscription - Network Infrastructure - Virtual Machines - Identity and Access - Security Monitoring | Yearly | proactive | Infotechtion | 40 | yes | NA | Azure architecture, Powershel, Azure devops, Key vault management, Azure firewall
12 | i-ARM Azure infrastructure | Windows patching, cumulative patches of the data gateway vm, updating the data gateway application, renewing client secrets and the related proces including testing across non-prod and prod environment. | Quarterly | proactive | Customer | 24 | No | yes | Device management, Azure cloud security.
13 | i-ARM Azure infrastructure | Activating and coordinating BCDR plan with cloud security , modern work and RIA team within customer environment. Note: i-ARM licensing includes addressing any product findings from the outcome of the exercise. | Yearly | proactive | Customer | 80 | No | yes | Azure backup, networking, high availability, i-ARM functional knowledge
14 | i-ARM Azure infrastructure | Coordination of technical change requests to process infrastructure or product feature changes, including binary hash in UAT / Prod as part of this process. | on-demand | reactive | Customer | 30 | No | yes | Customer CRQ process, Azure cloud security, powershell
15 | Microsoft Purview - Records Management | Create / update retention labels configurations approved by records manager | on-demand | reactive | Infotechtion | 5 | yes | NA | Microsoft Purview Records management technical expertise
16 | Microsoft Purview - Records Management | Review and support auto-labelling of files matching records criteria but not labelled in M365. | Monthly | proactive | Customer | 40 | No | yes | Microsoft Purview Records management technical expertise
17 | Microsoft Purview - Records Management | Provide Keyword query language support to records management team when working with eDiscovery. | on-demand | reactive | Customer | 4 | No | yes | Keyword Query Language, MS Purview eDiscovery technical expertise
18 | Microsoft Purview - Records Management | Review Purview records management role assignment is limited to authorized individuals. | Monthly | proactive | Customer | 2 | No | yes | Entra ID RBAC, MS Purview permissions management
19 | Microsoft Purview - Records Management | Migrate destroyed / active record metadata into a workspace (M365 Site etc.) integrated with i-arm, beyond the migration project scope. | on-demand | reactive | Customer | 30 | No | yes | M365 architecture, powershell.
20 | Microsoft Purview - Records Management | Adhoc requests to bulk reclassify records to support records management requirements or updates to bank's retention schedule. | on-demand | reactive | Customer | 35 | No | yes | Powershell, Graph API
21 | Microsoft Purview - Records Management | Recurring hands-on training on Microsoft Purview feature updates, roadmap to Records Management team on topics of Data lifecycle management, Records Mangement, eDiscovery, Subject Access Requests to Records Management team. | Quarterly | proactive | Customer | 8 | No | yes | Microsoft purview Records, data lifecycle, ediscovery, data explorer hands on experience.
22 | Microsoft Purview - Records Management | Integrating records management with existing Workspaces (M365 sites etc.) with files. | on-demand | proactive | Customer | 2 | No | yes | i-ARM standard procedures, powershel
23 | Workspace Governance | Review of Records Management enabled workspaces for compliance against Information Architecture (sample KPIS): - Workspaces with less than 2 or No Owner - Workspaces with No Retention labels published - Workspaces with records overdue disposition - Workspaces with Changes or removal of Hub association - Workspaces with unlabelled files | Quarterly | proactive | Customer | 20 | No | yes | powerbi, mgdc, powershell, azure synapse
24 | Workspace Governance | Develop adhoc workspace analytics reports to fulfill the key areas of responsibility related to RIA team. | Monthly | proactive | Customer | 20 | No | yes | powerbi, powershell
25 | Workspace Governance | Develop intelligent insights for storage optimization / Data obsolescence risk management. Including: - Redundant, Duplicate, Trivial data analysis - Files formats at risk of obsolscence - Files matching Sensitive / Personal Data classification and overexposed | Quarterly | proactive | Customer | 16 | No | yes | powerbi, powershell
26 | Workspace Governance | L2 / L3 support for service request related to changes require authorization as part of RIA team roles and responsibilities. Including: - Reuesting new labels to a workspace - Request removal of unused / unapplicable labels - Decommision / Archival process of an entire or subset of a workspace. | on-demand | reactive | Customer | 4 | No | yes | Microsoft purview Records, data lifecycle, ediscovery, data explorer hands on experience.
| Total Proactive |  |  | 14 |  | 611